## Sheet1
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE: memories application | [6 empty] | INSTUTUTE & DEPARTMENT NAME | [6 empty] | AP SHAH INSTITUTE OF TECHNOLOGY(Information Technology)
PROJECT GUIDE Prof.Manjusha Kashilkar | [6 empty] | DATE | [6 empty] | 2022-10-14
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PERCENTAGE OF TASK COMPLETE | PHASE ONE | [49 empty] | PHASE TWO
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 | [7 empty] | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Group formation and Topic finalization. Identifying the scope and objectives of the Mini Project | Hitesh Sachdev Siddhesh Sawan Aman Yadav | 2022-07-11 | 2022-07-22 | 2 | 100% | bar: WEEK 1 M to WEEK 2 F
1.2 | Identifying the functionalities of the Mini Project | Hitesh Sachdev Siddhesh Sawan Aman Yadav | 2022-07-25 | 2022-08-05 | 2 | 100% | bar: WEEK 3 M to WEEK 4 F
1.3 | Discussing the project topic with the help of paper prototype. | Hitesh Sachdev Siddhesh Sawan Aman Yadav | 2022-08-08 | 2022-08-19 | 2 | 100% | bar: WEEK 5 M to WEEK 6 F
1.4 | Designing the Graphical User Interface(GUI) | Hitesh Sachdev Siddhesh Sawan Aman Yadav | 2022-08-22 | 2022-09-09 | 3 | 100% | bar: WEEK 7 M to WEEK 9 F
1.5 | Presentation I | Hitesh Sachdev Siddhesh Sawan Aman Yadav | 2022-09-12 | 2022-09-16 | 1 | 100% | bar: WEEK 9 M to WEEK 10 F
2 | Project Design and Implementation
2.1 | Detail website Design | Hitesh Sachdev Siddhesh Sawan Aman Yadav | 2022-09-19 | 2022-09-23 | 1 | 100% | bar: WEEK 10 M to WEEK 11 F
2.2 | Integration of all Webpages | Hitesh Sachdev Siddhesh Sawan Aman Yadav | 2022-09-26 | 2022-09-30 | 1 | 100% | bar: WEEK 11 M to WEEK 12 F
2.3 | Report Writing | Hitesh Sachdev Siddhesh Sawan Aman Yadav | 2022-10-03 | 2022-10-07 | 1 | 100%
2.4 | Presentation II | Hitesh Sachdev Siddhesh Sawan Aman Yadav | 2022-10-10 | 2022-10-14 | 2 | 100% | bar: WEEK 13 M to WEEK 14 F